## techDocs2.0 Team
Name
PL
Yogesh (PL)
Frontend
Jacob (Lead)
Srilatha
Sasi Pritham
Sasidhar
Isha Jain
Nitish Reddy
Backend & Database
Bhavana (Lead)
Gadadhar
Prashant
Suravaram Radhika
Deployment
Arun (Deployment Lead)
Fatma
Munasib
Shritik Saxena
Ruchir
Integration
Preetham (Integration Lead)
Sahil Rai
Documentation
Sreelakshmi (Lead)
Shital
Manisha
Testing
Medha Gayatri
Analytics
Avadhesh (Lead)
Unavailable for Project
CVN Rao
Balu.86
Stayam Bhardwaj
Nitin Kumar
Desikan
Susmitha
Ajit
Ramya
Dnyanda

## Tasks
Sr. No. | Task | Assigned To | Updates
FRONTEND
1 | Login Validation not working | Srilatha
2 | Display loggedin username | Sasidhar | 3rd June: Pull requets merged into Main
3 | menu bar issue | Nitish / Sasidhar | 3rd June: Pull requets merged into Main
4 | Include additional templates | Jacob | Pending
5 | Grammar check | Isha / Yogesh | 1st June: Created basic front end design. Need to beautify it
6 | Plagiarism Check | Sasi Pritham/Yogesh/Nitish | 10th June: Integrated frontend and backend for plagarism check
7 | Navigation to Dashboard missing after login | Sasi
8 | revamp Homepage | Isha / Yogesh
9 | Refactor the frontend code | Yogesh
10
BACKEND
1 | Grammar Check | Bhavana / Yogesh | 31st May: Grammar Check endpoint created
2 | Plagiarism Check | Gadhadhar
3 | Store LaTex templates in Tables. Create endpoint for templates | Prasanth
4 | Dockerize API | Radhika / Avadesh / Yogesh / Fatma | 3rd June: Backend API running as Docker. Steps: 1. Pull latest changes from branch dockerize-backend-api. 2. Change "localhost" reference in .env.local file to "host.docker.internal". 3. Run the docker-compose file
5 | Resolve login bug | Preetham / Sahil
6 | Validation logic bug | Prasanth
7
8
9
10
DEPLOYMENT
1 | Explore auto deploy to EC2 instance | Fatma / Arun | Updates provided on daily calls betweem 27th May - 10th June
2 | Dockerize API | Fatma / Arun
3 | Dockerize FrontEnd | Fatma / Arun
4 | EC2 Instance Creation | Fatma / Arun / Yogesh
5 | EC2 Deployment usign NGING / GUNICORN Services | Fatma / Arun / Yogesh
INTEGRATION
1 | RAZORPAY iNTEGRATION - pAYMENT GATEWAY | Preetham / Sahil | Pending
2 | Create POST request for grammar check in editor.html file | Preetham / Yogesh | 3rd June: POST requets created. Response is also displayed in GUI. Check branch 5-grammar-check
3
TESTING
1 | Testing API Endpoints | Medha
2 | testing Grammer Check Fetaure | Medha
3 | Test FrontEnd / BackEnd integration | Avadesh
4
5
DOCUMENTATION
1 | Update Previous Documentation | SreeLakshmi / Shital
2 | Prepare Final PPT | SreeLakshmi / Shital
3
4
ANALYTICS
1